## Sheet1
		Worklog

Section		Task	Priority (1-3)	Deadline	Status

Parameters
		Nb of lines per page	2		100%
		Organise as a hierarchy	2		100%

Database
		Create indexes	3		0%
		Migrate to pg	2		100%

Objects
		Add Playground id as hierarchy first level	1		100%
		Bug in hierarchy calculation for territories and organisations, level to consider	1		100%
		Complete fileds of Business Object	1		100%
		Check updatable fields	2		0%
		Update Scopes functionalty	1		100%

Tests
		Check up in place tests	2		0%

Dimensions
		To develop	1		0%
		Tme Scales => form for generator

Layout and navigation
		Format code blocs as grey box	1		100%
		Route Back to list to the parent	1		100%
		Add units to the metrics => parameter for currency	1		100%
		When Business Objects are proposed for a Business Rule, limit the choice to the Business Objects of the same Business Area	1		0%
		Rename Route Back to Up	2		100%
		Create parameter for optional display of Assessment	2		100%
		Create Bread Scrums	1		0%
		Create Scopes for active records by Playgrounds	1		100%
		Add security linked to parameters (display_assessment, is admin) to controllers	1		100%
		Create help documentation	2		0%

Features
		Lists of values with mapping fonctionality	1		0%
		View on the Data Warhouse	1		0%
		RegEx helps identifying Br for external error messages